## Slide 1: Water Power Peer Review
SubTask CH TD 3.3.1.3 Day-ahead Scheduling and Real-time Operations Tool
Conventional Hydroelectric and Environmental Resource Systems (CHEERS) Model
Thomas D. Veselka
Organization: Argonne National Laboratory
Contact Info: tdveselka@anl.gov
Date: November 2, 2011
Laboratory Team:
Thomas Veselka (Hydropower Expert & Computational Engineer)
Mathew Mahalik (Power Systems & Computer Scientist)
Mark Jusko (Decision Analyst & Computer Scientist)
Day-ahead Scheduling and Real-time Operations

## Slide 2: Purpose, Objectives, & Integration
Improve the performance of hydroelectric and environmental resources through the development and application of an enhanced day-ahead scheduling and real-time operation tool
The tool is consistent with DOE’s objective to increase the contribution of conventional hydropower to the U.S. renewable energy portfolio
  Helps schedulers and operators improve hydropower efficiency, generating more power with the same amount of water
  Improves the economic value of both hydropower generation and ancillary services
  Strives to increase habitat quality
  Supports power grid operations, including wind and solar integration
  Provides cash-constrained organizations access to a cost-free tool
Integrate with other toolkit components by using:
  Inflows from the Hydrologic Forecast tool
  Daily and weekly water release targets from the Seasonal Hydro-systems Analysis tool
  Habitat parameters and relationships from the Environmental Performance tool
  Power characteristics from the Unit and Plant Efficiency tool
  Results for economic and environmental indicators posted to the shared DB

## Slide 3: Technical Approach
The design meets the requirements of a broad range of applications
  Network formulation represents the flow of commodities such as water and electricity
  Flexible scope and granularity in terms of time and space
  Accommodates a wide range of topology designs
  User-defined specifications
    System relationships & constraints
    Component attributes
    Boundary condition options
Simultaneously solves energy and environmental objectives
  Maximize production and economics within environmental operating constraints
  Optimize environmental quality, resulting in a temporal sequence of dam water releases
  Weighted multi-objective function

## Slide 4: Plan, Schedule, & Budget
Schedule
Initiation date: November 2009
FY2010
  CHEERS Model Framework and Design Document V1.0 September 2010
    Preliminary evaluation of mathematical techniques and solvers
    Preliminary tool interface and input templates
FY2011
  Preliminary proof-of-concept mathematics completed
  Complete tool functionality ready for application at demonstration sites
F2012
  Complete tool functionality ready for application at demonstration sites
  Demonstration site application and continued tool refinements
F2013
  Demonstration site application wrap-up and documentation
Budget
Less spent than budgeted
Additional staff have been recruited to assist with the tool GUI, DB, and model input forms
Budget History |  |  |  |  | 
FY2009 |  | FY2010 |  | FY2011/12 | 
DOE | Cost-share | DOE | Cost-share | DOE | Cost-share
550K |  | 550K |  | 550K (anticipated) | 

## Slide 5: Accomplishments and Results
Work in progress on the GUI and data input screens (behind original schedule)
  GUI manages project inventory (databases)
  Can create and edit nodes, links, and system data through GUI menus and spreadsheet forms
  Most spreadsheet input forms have been designed and implemented
  Most input forms are successfully linked to the GUI and the database
    Can load, edit, and save data successfully
  Database is mostly designed and implemented
    More tables need to be added and modified along with input form progress
  Input and result values can be displayed in the network along nodes and links
  Preliminary results spreadsheets have been created (e.g., energy balance, economic, unit dispatch, etc.)
Work in progress on the mathematical formulation (behind original schedule)
  Structure of the formulation and definition of equations is nearly complete
  A stand-alone model consisting of a single spread sheet and LINGO was developed for prototyping and testing
  Spreadsheet proof-of-concept for the formulation has been implemented
  GUI successfully linked to LINGO solver
  Work in progress on reading all data and creating all equations within the model
Interaction with demo sites and others in hydro industry (on schedule)
  Met with CDWR staff and toured demo site facilities. Also meet with WAPA schedulers and BOR plant dispatchers
  Preliminary topologies for both demo sites systems have been drafted. Document detailing CRSP operational practices and constraints has been completed
  Conducted web meetings with demo site staff and others to demonstrate model concepts, interface features, and receive feedback. Significant modification to operational rule approach based on feedback
  Secure file server in place and being used with sensitive demonstration site data

## Slide 6: Challenges to Date
“Fool-proofing” input forms
  Some possible user actions can cause errors or corrupt data
  For the time being we will warn users of such actions
Identifying all possible user actions and all data states when testing input form – database interaction
  Input forms may behave differently depending on what data is currently in the database
Optimization logistics
  Formulating the problem given the flexibility built into the input forms and modeling system
  Revisions of mathematical formulations may be required for more complex unit-commitment problems
  Need to explore alternative solvers including Dakota for consistency with the Seasonal tool, CPLEX, and gurobi

## Slide 7: Next Steps
CHEERS Data Collection
Finalize network drawings for each demonstration site and collect basic information. (12/31/2011)
In CHEERS, finalize and construct demo site topology with a finer level of granularity. (3/31/2012)
Collect real-time data for model applications. (7/1/2012 - 9/30/2012)
Toolkit Database (DB)
Given initial demo site data and toolkit implementation plans, meet with DB representatives from the 4-lab modeling team to identify outstanding DB requirements for toolkit applications. (12/31/2011)
Enhance the toolkit DB to accommodate demo site data and toolkit modeling requirements. (4/1/2012 - 8/31/2012)
Complete algorithms that expedite data transfers between demo site SCADA systems and the toolkit DB. (9/30/2012)
CHEERS Demo Site Applications
Using the GUI, create CHEERS topologies, perform preliminary optimization runs and analyze model results (12/31/2011)
Refine CHEERS implementations and add topology details as needed for day-ahead scheduling. (3/31/2012)
Continue to refine/improve day-ahead scheduling optimization. (6/30/2012)
Perform preliminary CHEERS application for real-time operations. (9/30/2012)
Finalize demonstration site day-ahead scheduling and real-time CHEERS model applications. (12/31/2012)
CHEERS Model Enhancements
Refine and debug spreadsheet input forms. (9/1/2011 - 12/31/2011)
On an ongoing basis work with demo site staff to identify and implement supplementary model features to meet the specific requirements of each site. (1/31/2012 - 10/31/2012)
Create auxiliary spreadsheet tools to aid with demo site applications. (7/1/2012 - 9/30/2012)
Refine spreadsheet input forms to accommodate demo site real-time data requirements. (7/1/2012 - 8/31/2012)
CHEERS Model Application and DB Documentation
Document CHEERS demo site applications and performance metrics. (2/28/2013)